## Final Log
|  | Project Name: | Whats app integration
Developers:
User stories log
Release | Nr | User Story | Description | DeadLine | Status
MINI Alfa ICT2-4 Weeks | 1 | Homepage | Product display |  | completed
| 2 | Measurement Form | Stiching measurement |  | completed
| 3 | Cart | Product added |  | completed
| 4 | Checkout | Form for card and shipping and customer details | 2019-04-18 | in progress
| 5 | Database | All Product details and card and customer details being stored. | 2019-04-25 | in progress
Beta ICT2 5 weeks | 1 | Admin Page | Customer Login as well as client login to make page dynamic. | 2019-05-03 | in progress
| 2 | App Design | Layout for app | 2109-05-10 | in progress
| 3 | Database | Database integrated with app. | 2019-05-17 | in progress
Final ICT2 | 1 | Testing (Databse) | All information is received and stored. | 2019-05-24 | in progress
| 2 | Testing (server) | Make website and app live on server. | 2019-05-24 | in progress
| 3 | Bug Fix | Fix all bugs or error | 2019-05-24 | in progress
Fix+B21:F24 all bugs or er

## App Desciption.
App Descrpition
1 | Login | registered member and new users
2 | Name of business(whats app grp) | list of business that work on whats app
3 | Member details | to get database client / owner has to give information of all member in their whats app group
4 | Join Groups | there will be option for user to send request to join any business/group.
5 | Registered member | my account will show which group they are in and can access website for those business.
6 | Link website | click of name of business they habe option to go to official website.
*It should be working as in the database and should cover all area about our projects
*Can take any 2-3 group with 5 member on it for showing how it works.